MAKERERE UNIVERSITY WALTER REED PROJECT

ANNUAL PROGRAM CLOSE OUT REPORT FOR FUNDING DURATION FY17/18 1ST OCTOBER TO 30TH SEPTEMBER 2018

BY

CHILD CARE AND YOUTH EMPOWERMENT FOUNDATION-CCAYEF

Introduction

Child Care and Youth Empowerment Foundation (CCAYEF), with support from Makerere University Walter Reed Project (MUWRP) has been  implementing HIV/AIDS Prevention activities i.e. DREAMS Project, HIV Prevention among KP/PP and OVC activities. The project aim is to reduce the incidence of new HIV cases among AGYW, KP/PP and OVC by 40%. The focus of the project was to reduce the incidence of HIV/AIDS through addressing structural drivers, done through various activities such as extensive HIV Counseling and Testing (HTS) outreaches; behavioral change classes referred to as stepping stones; Parenting and care giver programs(SINOVUYO), OVC empowermnet  and GBV care; Economic strengthening programs including; vocational skills training, financial literacy training, individual and small Village Savings and Loan Associations (VSLA); improved Contraception Mix, Peer to peer psycho-social support , PrEP promotion for Key and Priority populations, Condom Promotion & Provision and School Based HIV Prevention and family planning services.

Basing on the above preamble, this program close out report will be documented in two sections, i.e. Programming, and financial and audit sections.

- THE PROGRAMMING SECTION:

- PERFORMANCE UPDATE FY2017-2018

  - Project specifics

The project under reporting has been implemented for one year; from 1st October, 2017 to 30th September, 2018 although, some of the discussed project results encompass data of project year 2016-2017. The total project grant was 626,541,514/= and the project funding objective has been “To reduce the incidence of new HIV cases by 40%.” the project implementation area has been Mukono Central Division covering four (4) parishes and 27 villages.

  - OVERALL PROJECT ACHIEVEMENTS AGAINST ANNUAL SET TARGETS

    - Project overall target visa vi CSO achieved target

    - DREAMS (in school and out of school) and OVC target

    - KP/ PP and PrEP targets

  - . SPECIFIC PACKAGES’ PROVISION-STATISTICS PER TARGET CATEGORY

This section presents different packages and the number of beneficiaries per a specific package/service.

    - DREAMS (out of school AGYW and in school girls)

    - Orphans and other Vulnerable Children (OVC)

    - HIV prevention

PROJECT KEY ACHIEVEMENTS, CHALLENGES AND LESSONS LEARNT

Key Achievements:

- DREAMS PROJECT/ OVC ACTIVITY IMPLEMENTATION OUT-COMES

A mini Evaluation study of the DREAMS Project and OVC activities (FY2016-2017 and FY2017-April 2018) was conducted in April 2018 to establish the extent to which DREAMS and OVC activities have contributed to prevention/ reduction of incidences of HIV/AIDS infection among OVC and adolescent girls and young women in Mukono Central division. 144 AGYW in Central Division, aged 17-25 years old were interviewed in this evaluation study. The mean age of respondents was 22 years (St. Dev 2.45).  Majority of the girls had studied up to secondary school (67%), among which 98% were currently out of school by the time of this survey and 54 were working. Among the girls interviewed, 46% were single, 44% currently in sexual union. Fifty-nine percent of the girls interviewed were currently pregnant or carrying a baby already. In the same study, 122 client interviews were conducted with children and parents under the SINOVUYO project intervention. Qualitative interviews with selected stakeholders included 10 Key Informant Interviews (KII), 8 Focus Group Discussions (FGD), and 15 In Depth Interviews (IDI) of CCAYEF stakeholders, community leaders and local council leaders. KAB interviews for assessment of HIV/AIDS awareness intervention to keep HIV negative girls negative were conducted with 82 AGYW in-schools. 50 OVC Households were also interviewed to understand the impact of SINOVUYO sessions given to them.

- DREAMS ACTIVITIES:

Results:

- Keeping the HIV Negative Girls Negative:

In terms of increasing awareness of HIV/ AIDS and prevention of new infections, the project model indicated a success: Between October 2017-April 2018, there were 3 cases of AGYW whose HIV serological status turned from negative to positive among a cohort of 679 girls who had been enrolled in the project; two after 3 months of project start and one girl was found positive among 558 follow up tests done. Data from the excel sheet of this cohort indicates a rate of infection of 0.16% per annum. The project supported girls through intensive behavior change messages, kept the girls busy in training activities but also helped to empower the girls to safer sex negotiations including consistent use of condoms.

- Awareness about HIV/AIDS among AGYW:

When the AGYW were asked about their knowledge of HIV, 98% said were aware of HIV, 96.1% reported that un protected sex was the major cause of HIV infection, with over 57% indicating that multiple sexual relation is the major risk of acquiring HIV, 15% drug and substance abuse.

About HIV prevention, 92% mentioned use of condom as the main prevention mechanism, 6% said one can prevent HIV by abstaining.  The participants, who engaged in the focus group discussions, were aware of the availability of HIV/AIDS Counseling and Testing (HCT) services. On the other hand, discussants expressed sufficient knowledge about safe male circumcision and could encourage their men to have it done. The discussions also showed that awareness about PMTCT was relatively good. One respondent had this to say;

“At first I dint know how to protect myself. I feared to do HIV test. But after the first test, now I use protection all the time”.

- Assessment of Services Received from CCAYEF:

Asked what kind of services they received from CCAYEF, 34% of the interviewed girls obtained vocational training (hair dressing, tailoring, decoration and flower arrangement); 42% HIV counseling and testing, 21% were linked to any other health care service, 10% supported through VLSA, 6% any form of income generating activity. However 86% said they went through transitioning support, meaning that they went through a series of interconnected support, which began from HIV testing to other related activities.

- Economic Strengthening:

This evaluation interacted with some of the girls who went through DREAMS Project and they had this to say:

“I have now changed by behaviors. The way I used to carry myself and act is now different. At least I can make some money and take care of myself. I don’t depend on a man to live”. One of the girls talked to, during an in-depth interview.

Another respondent had this to say;

“Madam can’t you see how I look like? Before I came to CCAYEF I dint have hope, but now life has changed. I look really good. I have a small work I am doing. I am planning to go back to school. I want to study. Madam I want to study”. This was a powerful testimony from one of the beneficiaries of CCAYEF program.

- Village Saving and Loans Association (VSLA) Methodology

In the period under review, CCAYEF has established over 30 VSLA groups, and has supervised other 28 groups formed in Project year 2016-2017. Out of all the AGYW VSLA groups, 15 groups shared out. When members received their savings, 157 established own businesses, some bought Bitenge materials, made different designs out of them and started selling. Others made businesses ranging from selling animal feeds, to selling clothes and salons. 169 girls joined other community VSLA groups and started saving money again. Among the OVC household VSLA groups, 7 groups with 210 members shared out their money after the first cycle and entered into the second saving cycle. 108 established different businesses out of the money they shared and 107 have accessed loans from their saving groups to pay fees for their children.

- Vocational Skills Training and AGYW Employability

During the mini-evaluation study, out of the 144 AGYW who participated in the study, 103 said they had no jobs by the time of entry into the project, but at the time of assessment78 reported having jobs ranging from working in a salon, tailoring shops to being business women. They mentioned that the life skills they had acquired during the project had changed their interpersonal relations and could ably get a job or create one.

- Contraception & Family Planning Service Provision:

Contraceptive education to AGYW has been provided to discuss methods of contraception, how such methods are used and the effectiveness of each in preventing unintended pregnancy. 386 AGYW received information on family planning methodology and 39 others received services from VHTs and other qualified medical personnel.

- THE OVC ACTIVITIES

Achievements:

- Home visits to provide Adherence assessment, counseling for OVC households:

In this activity household vulnerability status assessments were done in; Economic strength, Food and nutrition security, Health, Water and sanitation, Child protection and legal support.  555House hold development plans were developed, and out of those, 200 HH realized theirs and are able to sustain their families and 122 OVC with unknown status were tested for HIV and their HIV status is now known.

- Increased capacity of OVC households to enroll and retain OVCs in Educational institutions:

This intervention was aimed at keeping the very vulnerable children in school until their parents and care takers are fully empowered to support them. The parents were trained in VSLA methodology, and by close of project 391 pupils were supported with school fees and 70 caretakers of these children are now able to continue providing their children with school fees and other needs and they also drew their sustainability development plans which included the following;

- Food preparation demonstrations in OVC communities:

This activity was conducted among 205 households to boost nutritional levels of the children in OVC HHs thus preventing them from getting malnourished. Results from a continuous assessment done using a MUCA tape indicate that 75 out 205 children now have a normal growth rate. Backyard gardens have also boosted OVC HH incomes leave alone nutrition. A one beneficiary has this to say;

Our diet improved because before I could not afford to buy vegetables. I earn 60,000 from the sale of sukuma per month. This has enabled me to provide basic needs for my family and pay part of school fees for my child. I thank CCAYEF for giving me an income generating activity.

- The impact of the SINOVUYO parenting sessions to OVC Households:

In the min-evaluation study, 50 OVC Households were sampled, out of these, 44 reported having better and constructive relationships with their children, favoring their growth and development. This was a result of the SINOVUYO sessions they received.

- HIV PREVENTION ACTIVITIES AMONG KP/PP

Achievements:

- Improved behavioral practices and perceptions among the KP/ PP:

Since the introduction of the HIV prevention program among the KP/PP, a number of key priority populations (CSW) have acquired a positive attitude towards PrEP, and condom use. This is visible in the number of phone calls their peers make to refer peers for PrEP services, requesting for condoms.

    - Key Challenges: The most pressing ones were;

Delay in delivering VSLA tool kits has been quite a challenge; this has de-motivated many girls from saving for they feel their money is unsecure; Lack of IEC materials carrying healthy related information for distribution to different category groups; Stock out of testing materials ( gloves, cotton, alcohol swabs , testing kits etc)has been a hindered some of the planned outreaches most especially during the KP, PP HTS; Unclear and ever changing project and program targets and instructions; Some MUWRP staff were a little impolite; In school target has been “half reached”  due to delay in training of SINOVUYO facilitators who are key in providing that services which is the entry point for any in school DREAM girl, it’s a challenge to report since it has affected our score card; Re- location of some OVCs, many OVCs move from one place to another looking for affordable accommodation, has affected the follow up and supervision process; Too many OVC activity tracking tools and yet some provide or capture the same information.

    - Lessons Learnt/ good practices

- Provision of STI drugs/ treatment for KPS during outreaches has seen to  a major incentive to attract a number of them to come for the HCT services; and Commitment to a well understood task yields results.

  - PARTNERSHIPS BUILT AND PROPOSED SUSTAINABILITY PLAN FOR BENEFICIARIES

    - Partnership built

During the implementation process of the DREAMS, OVC, PrEP, HIV prevention Activities’ CCAYEF has had an opportunity to develop partnership with different public and private sectors. These include community schools where it has been implementing OVC project activities, Health facilities like Kyungu HCII, District and Municipality line departments, Ministry of Gender, Labor and Social Development, local community leaders-the Local Councils, Civil Society Organizations; women leaders, men and the entire community.

Sustainability plan

The project has been built on community existing structures like schools, health facilities, and community leadership; this has been built through strengthening their capacities in managing and handling various project activities. For sustainability of the project, in schools the teachers who were trained in offering various project packages like SINOVUYO and SFI will work as facilitators and change ambassadors in their respective schools hence the acquired skills and knowledge will remain in the school and live beyond project period. Among out of school AGYW peer mentors trained shall stay passing on various behavioral change massage to their peers and CCAYEF, being a resident organization and having other projects that target the same type of population will monitor the mentors’ interventions. CCAYEF offices and two safe spaces will still work as safe spaces for girls and referral points for men, boys and other clients for service. Through continuous  referrals CCAYEF has been in position to popularize the youth corner at the Mukono health center IV and community project beneficiaries can now voluntary at own will move in and seek health attention.

  - Conclusion and way forward

    - Conclusion

Every journey that begins ends, the measure of its worth depends on the owner and the concerned, CCAYEF extends her gratitude to MUWRP and all other stakeholders in the implantation of the DREAM , OVC, HIV prevention project 2017/2018 for all the support extended to us financially, intellectually and emotionally.as any performing team we had challenges on both sides, however as human beings challenges to human and are healthy!The implementation of this project has not left us the same, we are very many steps a head especially; our capacity to handle projects has been greatly built.

Way forward

Going forward, CCAYEF wish to highlight different points to put in observation, the success of every project depends on how the implementing team understands it; it depends on good communication between implementing team and the project donor partner, clear objectives and goal. Therefore CCAYEF recommends that MUWRP fully orient sub grantees on the above mentioned issue. If there is any other opportunity to work with CCAYEF or any other partner, let MUWRP clearly share the project document and most especially the M&E plan such that any partner can easily work towards achieving on behalf of MUWRP.

Human resource

CCAYEF in the due course of its implementation of MUWRP funded project 2017/2018, it had the following people as directly grant paid staff and all these people have been retained in CCAYEF to support in implementation of other on-going and  upcoming projects.

| NO | Name | Title | Current salary |
| --- | --- | --- | --- |
| 1 | Ms. Proscovia Nalwadda | Project coordinator | 385,220/= |
| 3. | Mrs. Judith Katongole | Finance officer | 309000/= |
| 2 | Ms. Ruth Namusisi | Project officer | 309000/= |
| 3 | Mr. Osman Ganafa | Project officer | 309000/= |
| 4 | Mr. Francis Bulega | Project Officer | 309000/= |
| 5 | Mr. Joseph Baliruno | Data officer | 300,000/= |
| 6 | Nakabanda Joyce | OVC officer | 300,000/= |
| 7 | Ms. Lydia Nalule | Vocational Skills Program Trainers | 250000/= |
| 8 | Ms. AminaNakaweesi | Vocational Skills Program Trainers | 250000/= |
| 9 | Ms. Gloria Nalwanga | Vocational Skills Program Trainers | 250000/= |
| 10 | Ms. RestyNaabulime | Vocational Skills Program Trainers | 250000/= |
| 13 | Ms. NamutebiAnnet | Vocational Skills Program Trainers | 250000/= |
| 14 | Ms. NakawunguTeopista | Vocational Skills Program Trainers | 250000/= |
| 15 | Namubiru Sarah | AGYW Facility identify | 166,000/= |
| 16 | AlabaBrendah | AGYW Facility identify | 166,000/= |
| 17 | NantezaMilly | Community volunteer | 100,000/= |
| 18 | NakibukaRehema | Community volunteer | 100,000/= |

- Data management, transition and storage

In the project under reporting CCAYEF has been using various data collection tools in executing different activities, individual project beneficiaries ranging from OVCs and AGYW has individual files in which they information is kept.

DATA MANAGEMENT PLAN

Project data shall be transferred into an EPI info data base for it to be analyzed for effective usage and dissemination. Hard copies; registers and other data materials after transferring the data into EPIinfo they shall be delivered to MUWRP offices, Mukono.

Plans for archiving and preservation of project data:

Project data in hard copy shall be stored in data cabins before handing it over to MUWRP, the stored data shall be only accessed by data people or any other responsible person at the organization. It shall be accessed by outsiders on request and through signing a consent confidentiality form. CCAYEF will share data with all stakeholders. All personal client files shall remain in safe custody with CCAYEF to support review and follow-up of all CCAYEF clients/beneficiaries. Below is a table that shows the number of beneficiary files, location, number of registers and type;

| Program | No. of beneficiaries | No. of files | Location of files |
| --- | --- | --- | --- |
| OVC HH Individual files | 1926 | 1926 | CCAYEF Head Offices |
| DREAMS Individual Files | 815 | 815 | CCAYEF Head Offices |
| Project Registers by type |
| Name of Register | No. of registers | Where to be transitioned |
| SINOVUYO Registers | 12 | MUWRP Offices |
| DREAMS Activity Contact Register | 06 | MUWRP Offices |
| Stepping Stones Booklet | 03 | MUWRP Offices |
| DREAMS Service Provision Register | 06 | MUWRP Offices |
| Condom Distribution Register | 01 | MUWRP Offices |
| GBV Register | 01 | MUWRP Offices |
| DREAM Male Partner Characterization Among AGYW Groups Register | 01 | MUWRP Offices |
| AGYW Identification Register | 01 | MUWRP Offices |
| Integrated OVC registers | 04 | MUWRP Offices |
| OVC Longitudinal Service Register | 06 | MUWRP Offices |

Data transition process

Data shall be transitioned to MUWRP offices one month after the completion of the project, in this one month the CCAYEF data team will have been through with all data cleaning. If need be, and it is a must, individual files will go to the District/Municipality CDO.

- Financial and audit section

Summary of financial reports for each grant year

| FY | 2016/2017 |  | 2017/2018 |
| --- | --- | --- | --- |
| Contract grant | 125,547,548 | Contract grant | 876,043,979 |
| Addendum grant | 161,371,906 | Addendum grant | 0 |
| Q1 funds disbursed | 35,001,550 | Q1 funds utilised | 16,622,937 | Q1 funds disbursed | 263,205,561 | Q1 funds utilised | 154,319,949 |
| Q2 funds disbursed | 105,511,232 | Q2 funds utilised | 69,243,050 | Q2 funds disbursed | 227,413,184 | Q2 funds utilised | 154,319,949 |
| Q3 funds disbursed | 73,787,136 | Q3 funds utilised | 58,246,544 | Q3 funds disbursed | - | Q3 funds utilised | 180,723,990 |
| Q4 funds disbursed | 45,658,000 | Q4 funds utilised | 80,053,010 | Q4 funds disbursed | 135,922,769 | Q4 funds utilised | 137,153,376 |
| Total | 259,957,918 | Total | 224,165,541 | Total | 626,541,514 | Total | 626,517,264 |
| Balances |  |  | 35,792,377 | Balances |  |  | 24,250 |

Asset register

The table below highlights the assets records

| Item description | Serial no. per item | No. of items | CURRENT STATUS | ACQUISITION | ASSET TYPE | CURRENT LOCATION OF THIS ASSET |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Functional | Non-functional | Date of acquisition | Purchase value | Fixed | Not fixed |  |
| Wall drier | CCAYEF 2S | 1 | Functional |  | 11/1/2017 | 370000 | Fixed |  | Hair dressing room |
| Steamer | CCAYEF 5S | 1 | Functional |  | 17/1/2017 | 330,000 | Fixed |  | Hair dressing room |
| Fire extinguisher |  | 1 |  | Non-functional | 8/10/2016 | 160,000 | Fixed |  | Corridor |
| Plastic chairs | CCAYEF (1-100) | 61 | Functional |  | 31/10/2016 | 719,200 | Fixed |  | Safe spaces |
| Table | CCAYEF 9B | 1 | Functional |  | 23/2/2017 | 70,000 | Fixed |  | Tailoring room |
| Knitting machines |  | 2 | Functional | Non-functional | 17/3/2017 | 1,200,000 | Fixed |  |  |
| Tables | CCAYEF 10B &11B | 2 | Functional |  | 17/3/2017 | 140,000 | Fixed |  | Tailoring room |
| Sink | CCAYEF 3S | 1 | Functional |  | 24/3/2017 | 140,000 | Fixed |  | Hair dressing room |
| Stool | CCAYEF 11F | 1 | Functional |  | 24/3/2017 | 10,000 | Fixed |  | Tailoring room |
| Plastic seats | CCAYEF | 100 | Functional |  | 18/4/2017 | 1,200,000 | Fixed |  | CCAYEF premises |
| Printer and Computer | CCAYEF 1P & CCAYEF 6D |  | Functional |  | 28/4/2017 | 6,472,300 | Fixed |  | Data office and Finance and Administration office |
| Sewing machines | CCAYEF 1H-4H | 4 | Functional |  | 28/4/2017 | 1,500,000 | Fixed |  | Tailoring room |
| Sewing machine | CCAYEF 5H-10H | 5 | Functional |  | 2/8/2017 | 2,580,000 | Fixed |  | Tailoring room |
| Sewing machines | CCAYEF 11H-13H | 3 | Functional |  | 13/12/2017 | 1,410,000 | Fixed |  | Tailoring room |
| Gray Plastic chairs | CCAYEF (1-25) | 25 | Functional |  | 28/7/2018 | 500,000 | Fixed |  | CCAYEF premises |

Work spaces

| Period | Name of safe space | Location | Function | No. of beneficiaries | Bills catered for by the grant |  |
| --- | --- | --- | --- | --- | --- | --- |
| 2017-2018 | Namumira | Namumira | Vocational training centre | 418 | 6,000,000 |  |
|  | Kyungu | Kyungu | Vocational training centre | 124 | 4,800,000 |  |
|  | Ntawo/Kasangalabi | Ntawo and Kasangalabi | Vocational training centre | 113 | 4,800,000 |  |
|  | Lweza | Lweza | Vocational training centre | 160 | 4,800,000 |  |
| Period | Name of Apprenticeship site | Location | Function | No. of beneficiaries | Bills catered for by the grant |  |
| 2017-2018 | KK Decorators and Function hire services | Mukono town | Flower arrangement and Decoration | 22 | 3,600,000 | 3rd and 4th qtr |
|  | Tufanyekazi social development Association | Mukono | Craft training in textile and Back cloth making | 10 | 9,000,000 | 1st, 2nd and 3rd qtr |
|  | David Art And Craft Workshop | Mukono |  | 6 | 5,400,000 | 3rd qtr |
|  | Gifted hands | Mukono | Jewelry making | 27 | 2,700,000 | 4th qtr |
|  | Mothers' Union | Mukono | Liquid soap making | 25 | 2,500,000 |  |
|  | Institute of professional studies Mukono | Mukono | Catering | 2 | 1,800,000 |  |

Work space transition / close out plan

| S/N | Safe space | Transition plan | Payment status | Evidence of payment |
| --- | --- | --- | --- | --- |
|  | Kyungu safe space | This safe space is closed down , all girls are redirected to Namumira safe space for vocational studies those that joined later in May/June | This safe space has been directly paid using project contract money, and all months October 2017-september 2018 have been fully paid | Rent payment receipts |
|  | Namumira safe space | This being CCAYEF main office the safe space will remain opened and girls from different safe spaces will utilize it for trainings | This safe space has been directly paid using project contract money, and all months October 2017-september 2018 have been fully paid | Rent payment receipts |
|  | Ddandira safe space | This safe space is close and AGYW redirected to join Namumira safe space, due to lack of funds to continue paying rent | This safe space has been directly paid using project contract money, and all months October 2017-september 2018 have been fully paid | Rent payment receipts |
|  | Ntawo safe space | This safe space shall stay in existence as part of CCAYEF prject sustainability plan. | This safe space has been directly paid using project contract money, and all months October 2017-september 2018 have been fully paid | Rent payment receipts |

Appendix

Appendix 1. SUCCESS STORIES

Story #1: HIV PREVENTION, CARE AND TREATMENT:

John Opoda (pseudo names) a father of 4 children and a wife (in a discordant relationship) was diagnosed with HIV 2 years ago and initiated on ART but after some time, he lost hope and withdrew from treatment. His condition worsened and eventually got AIDs. However during the follow ups for those clients who are lost to follow up, John was identified, given support and adherence counseling and encouraged to get reinitiated on ART for a better health. He eventually accepted to be re-initiated. The client is still under CCAYEF’s close monitoring for proper adherence.

Story #2

Under the prevention program, we offered adherence counseling to one of our positive client who had started on drugs but after sometime, abandoned treatment. Definitely, her health started deteriorating. This client-Jesca (Pseudo name), 28 years, a resident of Gulu A, Gulu ward was discovered through the routine follow-ups made to our clients with the help of our Facility Linkage Facilitator. She had reportedly missed her appointments for two consecutive months citing reasons of drug side effects and lack of transport to the facility. She was given adherence and support counseling and accepted to be re-instated on treatment. The FLF continuously followed up and supported her. Her family was also encouraged to support her through taking her medicines. It is now close to 2 months with a stable situation.

Story #3: GBV

Shillah (Pseudo name) 31 a KP from one of the hot spots was assaulted by the purported customer after the two failed to agree on payment modalities. The victim had requested for extra fee which the suspect declined and he started assaulting her physically and sexually. The neighbors and our KP peer leader came to her rescue and our staff was called and intervened, took the suspect to police, secured medical forms and examination, facilitated her and got the police surgeon’s report which eventually clearly indicated the proof of both physical and sexual assault. The suspect was later released on police bond and failed to report to police on the agreed dates however with the efforts from CCAYEF staff, the police was put to task to look for and produce the suspect since all the necessary documents including recording statements from both the victim and the witnesses had all been secured. The suspect was later arrested and under the police detention.

Story #4: VSLA:

Janny (Pseudo), a mother of 6 children is a member of Basooka kwavula VSLA group in Lweza. She started saving with 2 shares (4000) then later increased to 4 and 5 shares. She increased her saving capacity after discovering that she can as well borrow from the group to supplement on her small scale business.

She later started borrowing and added on the 6 goats’ project by adding 2 to make a total of 8 goats. She later sold some and paid school fees for her child. Presently she is so happy because one of her goats had produced 2 kids and another one had also produced one kid.

Janny’s Goats and pigs

Several other VSLA groups have shared out money including; The Rock VSLA group, Ssuubi VSLA group, Arise and Shine VSLA group (3155000);, Empowered  VSLA group, Winners VSLA group, and Agali awamu. These are both AGYW and community OVC HH groups. Agali awamu had 2974 total number of shares. Before sharing out, the group was trained on how to share out the money. And total interest realized was 594,000 out of the 45 number of loans. The group made no losses.  Most of the groups have resumed saving and others have joined other VSLA groups, but others have also become village mobilizers; putting other women and men into groups and inviting CCAYEF staff to train them!

Story #5

Juliet24, a mother of 2 children is a hair dresser who underwent VSLA training as she was doing her course in hair dressing. She started saving with Empowered VSLA group that shared out in December and at the end of the course she had saved 130,000 which had accumulated 17,000 profits. Alongside hairdressing, she invested her money in a business of a stall where she sells tomatoes, onions, and silverfish among others. She earns 3000 per day from her business which is approximately 90,000 per month and she is able to supplement on her need and take her elder child to school since her husband is not working as she claims.